## Cover
GRAC Asset & Contract Management -- UAT Test Cases (Phase 9)
Module | Asset & Contract Management (BRD v1.7), migrations 420-453
Scope | Permissions and organization isolation, workflows, reconciliation, report catalogue / export / distribution, regression of every asset screen.
Depth | Functional happy paths plus negative, segregation-of-duties, data-scope and reconciliation cases.
Scripts | database/deployment/16_UAT_Diagnostics_AssetContract.sql (read-only) and 17_Asset_Contract_Regression_Tests.sql (UAT only).
Prepared | Draft for UAT -- fill Status (Pass / Fail / Blocked) and Remarks per execution run.
Legend
Type | Functional, Negative, Validation, Permission, SoD (segregation of duties), Isolation, Data scope, Reconciliation, Security, Regression
Priority | High = core flow / blocks UAT if broken; Medium = important, has a workaround; Low = cosmetic
Status | Edit only column J of each sheet: Pass / Fail / Blocked (blank = not run). The summary below counts them.
Summary
Sheet | Cases | Pass | Fail | Blocked | Not run
AC Permissions | 18 | 0 | 0 | 0 | 18
AC Workflows | 13 | 0 | 0 | 0 | 13
AC Reconciliation | 10 | 0 | 0 | 0 | 10
AC Reports & Delivery | 13 | 0 | 0 | 0 | 13
AC Regression | 20 | 0 | 0 | 0 | 20
Total | 74 | 0 | 0 | 0 | 74

## AC Permissions
Asset & Contract -- permissions and organization isolation
Who may open, change and approve each screen; the Web proxy and the procedures refuse the rest (403 / error number).
TC ID | Screen / Menu | Scenario | Type | Priority | Pre-conditions | Test Steps | Test Data | Expected Result | Status | Remarks
ACP-001 | All asset screens | Screen hidden without VIEW | Permission | High | Role without VIEW on Asset Register | 1. Remove asset-register VIEW in Role Master 2. Re-login 3. Open the Asset & Contract menu | Test role | Asset Register is not in the menu; opening /Practice/Index/asset-register directly is refused.
ACP-002 | All asset screens | Other organization refused | Isolation | High | User mapped to organization A only | 1. Call a list URL of any asset screen with organizationId of organization B (browser address bar / dev tools) | organizationId of B | HTTP 403 "Caller is not authorised for the requested organization."; no rows of B appear.
ACP-003 | Asset Register | New asset needs ADD, change needs EDIT | Permission | High | Role with VIEW + EDIT, no ADD | 1. Try to create an asset 2. Edit an existing asset | - | Create refused (403); edit saved.
ACP-004 | Asset Register | Lifecycle approval needs APPROVE | Permission | High | Lifecycle change awaiting approval; role with EDIT, no APPROVE | 1. Open the pending change 2. Approve | - | Approve / Reject refused (403); Cancel allowed with EDIT.
ACP-005 | Asset Register | Valuation method override needs APPROVE | Permission | Medium | Asset with Asset Value; role with EDIT only | 1. Valuation tab -> override method | - | Refused (403); Recalculate (EDIT) allowed.
ACP-006 | Asset Attestation | Only the assignee responds; only the manager decides | Permission | High | Attestation assigned to employee X; manager M | 1. As another employee with VIEW, respond 2. As X respond 3. As someone other than M approve | - | Step 1 refused by the procedure; step 2 saved; step 3 refused. Cancel needs APPROVE.
ACP-007 | Asset Attestation | Exception approve / reassign need APPROVE; investigator actions only by the investigator | Permission | High | Open verification exception with an investigator | 1. As a non-investigator with VIEW, start investigation 2. As investigator start 3. Approve resolution without APPROVE | - | 1 refused, 2 saved, 3 refused (403).
ACP-008 | Asset Contracts | Segregation of duties on contract versions | SoD | High | Version submitted by user S | 1. As S review / approve the version 2. As another user with APPROVE approve | - | S is refused by the procedure; the other user approves.
ACP-009 | Asset Contracts | Vendor contact validation by someone other than the creator | SoD | Medium | Contact mapping created by C | 1. As C validate 2. As another user with APPROVE validate | - | C refused; other user validates.
ACP-010 | Asset Relationships | Proposal ADD, change EDIT, approval APPROVE (not the proposer) | SoD | High | Relationship proposed by P | 1. As P approve 2. As another approver approve | - | P refused; approval by another user activates it.
ACP-011 | Asset Discovery | Accept observed value needs APPROVE; execute merge needs Asset Register EDIT | Permission | High | Open conflict; approved merge | 1. Accept observed value with EDIT only 2. Execute merge without asset-register EDIT | - | Both refused (403).
ACP-012 | Asset Privacy | Privacy exception approve needs APPROVE; Extend outcome needs APPROVE | Permission | High | Exception requested by R; open retention review | 1. As R approve 2. Complete review with Extend without APPROVE | - | 1 refused (segregation), 2 refused (403); other outcomes with EDIT saved.
ACP-013 | Asset Taxonomy | Global taxonomy only by platform administrator | Permission | High | Organization admin (not PM_ADMIN) with taxonomy EDIT | 1. Add a category | - | Refused: "only the platform administrator can change it". Organization defaults of a type can be saved with EDIT.
ACP-014 | Technology Catalogue | Shared catalogue only by platform administrator | Permission | Medium | Organization admin | 1. Save a model with Shared ticked | - | Refused (403).
ACP-015 | Asset & Contract Dashboard | Sections follow screen permissions | Permission | High | Role with VIEW on Asset Register and Asset Contracts only | 1. Open Asset & Contract -> Dashboard | - | Only the asset / technology and contract sections appear.
ACP-016 | Asset Reports | Report list limited to viewable screens | Permission | High | Role with Asset Reports + Asset Register VIEW only | 1. Open Asset Reports -> Catalogue 2. Call /reports/CON_EXPIRY/run directly | - | Only Asset, Technology, CIA reports listed; direct call returns 403 (53103).
ACP-017 | Asset Reports | Restricted export needs APPROVE | Permission | High | Settings: a report set to RESTRICTED (policy default Approver) | 1. As a user without Asset Reports APPROVE export it 2. As an approver export it | - | 1: "Export ... needs Asset Reports APPROVE" (403, 53105). 2: CSV downloaded and recorded.
ACP-018 | Asset Reports | View Data Scope applies to report grid and export | Data scope | High | Role with a restricted View Data Scope on risks | 1. Run Inherent/Residual Risk 2. Export it | - | Grid and file show only risks in the scope; the counts match.

## AC Workflows
Asset & Contract -- workflows end to end
Life cycles that cross screens and people; each step leaves an audit row (practice_audit_trace / history tabs).
TC ID | Screen / Menu | Scenario | Type | Priority | Pre-conditions | Test Steps | Test Data | Expected Result | Status | Remarks
ACW-001 | Asset Register | Register an asset from Draft to Active | Functional | High | Asset type with an approved form template | 1. New asset -> fill mandatory fields -> Save 2. Transition to Active (approval if the gate needs it) | Asset type with template | Asset saved in Draft; mandatory-field check blocks incomplete moves; Active after approval; history shows each move.
ACW-002 | Asset Register | Lifecycle gate blocks a move | Validation | High | Asset with a BLOCK privacy gap or an active critical relationship | 1. Move to Active (privacy) or Disposed (relationship) | - | Move refused with the reason naming the gate.
ACW-003 | Asset Attestation | Periodic attestation to closure | Functional | High | Attestation profile for the asset type; asset with custodian | 1. Generate (campaign) 2. Assignee confirms 3. Manager approves | - | Pending -> Confirmed -> Closed; next attestation date set; overdue occurrences show Overdue after the due date.
ACW-004 | Asset Attestation | Disagreement raises a verification exception | Functional | High | Open attestation | 1. Respond Disagree, category Asset lost 2. Investigator resolves with Lost confirmed 3. Approver approves; close | - | Exception routed per rule; SLA dates; lost-asset security review required before closure; asset can move to Lost.
ACW-005 | Asset Contracts | Contract version to Active and renewal | Functional | High | Vendor, coverage type option | 1. Create contract and version, submit, review, approve (different users) 2. Effective start reached (scheduler) 3. Renewal opens at the notice date | - | Version Active on its start date; previous version superseded; renewal occurrence opened and approvable.
ACW-006 | Asset Contracts | Coverage requirement gap | Functional | Medium | Coverage requirement REQUIRED for an asset type | 1. Asset of that type without coverage 2. Add a contract covering it | - | Gap listed (Missing), then cleared when covered; Short when shorter than the minimum period.
ACW-007 | Asset Notifications | Reminder and escalation | Functional | Medium | Notification profile for contract expiry with stages | 1. Contract ending inside the first stage 2. Run the scheduler | - | Occurrence opened; in-app notice in My Notifications; escalation level rises per stage; snooze needs the configured role.
ACW-008 | Asset Activities | Calibration result with failed outcome | Functional | Medium | Recurring calibration activity | 1. Complete with Failed result 2. Review the restrictive-use review | - | Disposition required; restrictive-use review opened; reviewer other than submitter.
ACW-009 | Asset Relationships / Business Services | Service with supporting items | Functional | Medium | Business service | 1. Map assets as Supports Service 2. Approve relationships 3. Retire an asset that is a critical dependency | - | Topology shows items; retirement blocked until accepted.
ACW-010 | Asset Discovery | Ingest a batch and reconcile | Functional | High | Discovery source with rules | 1. Import CSV batch 2. Resolve suggested match, conflict and duplicate | CSV with externalKey | Matched links updated; conflicts queued; duplicates merged through Merge (approval + execute) with recovery available.
ACW-011 | Asset Privacy | Exception, review and retention | Functional | High | Asset with personal data Yes | 1. Record a masking gap exception (request -> approve by another) 2. Let the review date pass; complete review | - | Status Conditional while excepted; review completed with outcome; retention end computed.
ACW-012 | Asset Valuation | Configuration version and recalculation | Functional | Medium | Valuation configuration with bands | 1. Approve a new configuration version 2. Run the impact analysis and recalculation with a reason | - | Stored values unchanged until the run; run moves categories as analysed; history kept.
ACW-013 | Asset Governance | Snapshot and late data | Functional | High | Organization with assets | 1. Take snapshot 2. Clear an owner; Take snapshot again 3. Take snapshot without changes | - | Version 2 of today supersedes 1 (kept); third returns "No change".

## AC Reconciliation
Asset & Contract -- reconciliation (BRD 13.4.1, 19.8)
The same number must appear on the screen, the dashboard and the report. Run database/deployment/16_UAT_Diagnostics_AssetContract.sql first: section 4 must be all PASS and section 5 gives the expected numbers.
TC ID | Screen / Menu | Scenario | Type | Priority | Pre-conditions | Test Steps | Test Data | Expected Result | Status | Remarks
ACR-001 | Diagnostics script | Script 16 reconciliation section all PASS | Reconciliation | High | 452 / 453 run | 1. Run 16_UAT_Diagnostics_AssetContract.sql for the organization | @organization_id | Section 4: R1-R6 PASS (SKIPPED allowed where no data); Section 3 shows no FAIL.
ACR-002 | Asset Register / Dashboard / Reports | Lifecycle status counts | Reconciliation | High | Script 16 section 5 | 1. Filter Asset Register by each status 2. Dashboard bar Assets by lifecycle status 3. Complete Asset Register report with the status | - | The three totals equal section 5 "Register status".
ACR-003 | Dashboard / Reports | Asset Value distribution | Reconciliation | High | Script 16 section 5 | 1. Dashboard bars Assets in use by Asset Value 2. Asset Value Distribution report | - | Equal per category and to section 5.
ACR-004 | Asset Attestation / Dashboard / Reports | Attestation display status | Reconciliation | High | - | 1. Asset Attestation filtered to Overdue 2. Dashboard Overdue tile 3. Overdue Attestations report | - | Same count (open and past due = Overdue).
ACR-005 | Asset Contracts / Dashboard / Reports | Coverage gaps | Reconciliation | High | - | 1. Coverage gaps tab 2. Dashboard Coverage gaps tile 3. Coverage Gaps report | - | Same count and same assets.
ACR-006 | Asset Privacy / Dashboard / Reports | Privacy status | Reconciliation | High | - | 1. Asset Privacy filtered by status 2. Dashboard bar 3. Personal-Data Assets report with the status | - | Same counts (report lists applicable assets only).
ACR-007 | Asset Discovery / Dashboard / Reports | Reconciliation queue by kind | Reconciliation | Medium | - | 1. Queue filtered by kind 2. Dashboard Open conflicts / duplicates 3. Reconciliation Queue report | - | Same counts.
ACR-008 | Asset Governance | Score = its record rows | Reconciliation | High | Snapshot taken | 1. Open a KPI detail 2. Add passing and failing contributions | - | Numerator and denominator equal the card; failing / excluded counts equal the rows.
ACR-009 | Asset Reports | Grid total = export rows | Reconciliation | High | Any report | 1. Run with filters; note the total 2. Export CSV | - | File Rows line and data rows equal the grid total; Export history shows the same filters and count.
ACR-010 | Asset Reports | Delivered file = recipient run | Reconciliation | Medium | Schedule with a recipient | 1. Run now 2. As the recipient run the same report with the schedule filters | - | Delivered row count equals the recipient grid total (same data scope).

## AC Reports & Delivery
Asset & Contract -- report catalogue, export, schedules (BRD 13.4)
Asset Reports screen. Automated counterpart: database/deployment/17_Asset_Contract_Regression_Tests.sql (UAT only, @confirm = 1).
TC ID | Screen / Menu | Scenario | Type | Priority | Pre-conditions | Test Steps | Test Data | Expected Result | Status | Remarks
ACD-001 | Asset Reports | Catalogue by family | Functional | High | Admin | 1. Open Asset Reports | - | Nine families; 47 runnable reports; 6 listed as not available with where the information is.
ACD-002 | Asset Reports | Run with filters and paging | Functional | High | - | 1. Open a report 2. Set status / asset type / dates / days 3. Page | - | Only the filters the report takes are shown; totals change with the filters; paging works.
ACD-003 | Asset Reports | Invalid filters refused | Negative | Medium | - | 1. From date after To date 2. Days 0 | - | Messages from 53106; nothing exported.
ACD-004 | Asset Reports | Export CSV watermark and record | Functional | High | Report allowed to export | 1. Export CSV 2. Open the file 3. Export history | - | First lines: classification, report and version, organization, exported by, UTC time, export ID, filters, rows; history row with the same data.
ACD-005 | Asset Reports | Formula-looking text is neutralised | Security | Medium | Asset named =1+1 | 1. Export Complete Asset Register | Asset name =1+1 | Cell shows '=1+1 as text in the spreadsheet.
ACD-006 | Asset Reports -> Settings | Disable / classify / policy | Functional | High | Asset Reports EDIT | 1. Disable a report 2. Set classification below default 3. Set policy Disabled | - | 1: cannot run (53104). 2: refused (53108). 3: Export button hidden; export refused.
ACD-007 | Asset Reports -> Schedules | Create schedule with distribution list | Functional | High | EDIT; employees and a role | 1. New schedule weekly Monday, keep 30 days, employee + role 2. Save | - | Next run = coming Monday (today if Monday); recipients listed.
ACD-008 | Asset Reports -> Schedules | Validation of schedule | Negative | Medium | - | 1. Save without recipients 2. Monthly day 29 | - | Refused (53125, 53124).
ACD-009 | Asset Reports -> Schedules | Run now and distribution result | Functional | High | Schedule with one permitted and one refused recipient | 1. Run now 2. Deliveries -> Recipients | - | Permitted DELIVERED with rows; refused SKIPPED with the reason (e.g. No VIEW permission on Asset Reports).
ACD-010 | Asset Reports -> My deliveries | Recipient downloads | Functional | High | Delivered file | 1. As the recipient open My deliveries 2. Download | - | CSV with watermark and Generated at line; download recorded in Export history; download count 1.
ACD-011 | Asset Reports -> My deliveries | Download re-checked | Permission | High | Delivered file; then remove the recipient report screen VIEW and re-login | 1. Download | - | Refused (403, 53129).
ACD-012 | Background worker | Scheduled delivery once per day | Functional | High | API running, AssetReportDeliveryEnabled = true | 1. Schedule due today 2. Wait for the pass (<= 60 min) 3. Wait for the next pass | - | One delivery started SCHEDULED; the next pass the same day starts nothing.
ACD-013 | Background worker | Retention removes files | Functional | Medium | Schedule kept 1 day | 1. Next day after the pass open My deliveries | - | File shown as Removed (retention); distribution result kept.

## AC Regression
Asset & Contract -- regression of every screen
Smoke pass after each deployment: every screen loads for the organization, lists page, the organization picker remembers the last choice.
TC ID | Screen / Menu | Scenario | Type | Priority | Pre-conditions | Test Steps | Test Data | Expected Result | Status | Remarks
ACX-001 | Dashboard | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-002 | Asset Register | Screen loads, lists and pages | Regression | High | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-003 | Field Dictionary | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-004 | Form Templates | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-005 | Valuation Configuration | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-006 | Option Lists | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-007 | Taxonomy | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-008 | Technology Catalogue | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-009 | Asset Attestation | Screen loads, lists and pages | Regression | High | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-010 | Asset Contracts | Screen loads, lists and pages | Regression | High | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-011 | Asset Notifications | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-012 | Asset Activities | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-013 | Asset Relationships | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-014 | Business Services | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-015 | Asset Discovery | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-016 | Asset Privacy | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-017 | Asset Governance | Screen loads, lists and pages | Regression | Medium | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-018 | Asset Reports | Screen loads, lists and pages | Regression | High | Organization with data | 1. Open the screen 2. Change organization 3. Page / search the main list | - | No error banner; rows for the chosen organization; the picker keeps the last organization.
ACX-019 | Database | Migration verification blocks | Regression | High | Deployment | 1. Run 420-453 in order 2. Read each verification block | - | Every verification row PASS.
ACX-020 | Database | Regression test script | Regression | High | UAT database | 1. Set @confirm = 1 in 17_Asset_Contract_Regression_Tests.sql and run | - | All tests PASS (SKIPPED only where the organization lacks a permitted / refused employee); test data removed.